**SINGLE IMPROVEMENT PLAN 2015/16 –GOVERNANCE SECTION (to be evaluated in June 2016)**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Action** | **Lead** | **Resources** | **Timescale** | **Monitored by** | **Monitoring** |
| * Develop the GB’s ability to scrutinise the school’s Performance Information and its understanding of ‘Assessment without levels’ so that the GB can enhance its monitoring and evaluation role, thereby driving school improvement
 | Chair of the Standards Committee & HT | Presentations at GB meetings.LDBS & HLT training | Autumn & spring terms | Standards Committee.Strategy Committee | GB Minutes. Training log. |
| * Ensure that the GB’s two main Committees remain quorate and are functioning well and that each is monitoring the relevant sections of the ‘Single Improvement Plan’
 | Chairs of the two Committees |  | Throughout the year | Strategy Committee | Committee minutes |
| * Ensure that there is structured feedback from children, parents and staff. Occasions for this to be timetabled into the school year
 | HT | Good practice from other schools. External providers eg ‘John Yates School Support Services Ltd’ | Feedback, analysis and action plan by May 2016 | GB | Questionnaires & reports. Headteacher’s analysis |
| * Aim to support Link Governors so that they can provide appropriate challenge and support to the school
 | HT & Chair | Good practice from other schools. LDBS and HLT advice | Throughout the year | Strategy Committee | Learning Walk reports |
| * Governors to ensure that Performance Management processes are being effectively used by leaders to impact on the quality of teaching and learning, thereby ensuring that pupil outcomes are improved.
 | Chair of the Resources Committee | Good practice from other schools. LDBS and HLT advice.Up to date performance information showing pupil outcomes. | Throughout the year | Resources Committee | Committee minutes |
| * Headteacher Performance Management undertaken within the recommended timeframe and to good effect.
 | Chair  | LDBS facilitator | Autumn term | Completion reported to full GB | Committee minutes |
| * Governors evaluate their action plan and revise it to ensure that they are holding the school to account.
 | Chair | Members of the Strategy Committee | Throughout the year | Strategy Committee | Committee minutes |
| * Governors to monitor the impact of pupil premium spending.
 | Chair of the Resources Committee | Members of the Strategy Committee. LDBS and HLT advice  | Throughout the year | Resources Committee | Committee minutes |